## Jira Import
Issue Type | Epic Name | Epic Link | Summary | Description | Acceptance Criteria | Priority | Labels | Sprint / Phase
Epic | AWS Compute Cost Optimisation Strategy (90-Day Operating Model) |  | AWS Compute Cost Optimisation Strategy (90-Day Operating Model) | Implement a governed, metrics-led operating model to reduce AWS EC2/VM compute cost by 30-40% within 90 days across R&D, SaaS and departmental installations without causing critical incidents. Recommendations are evidence-backed; production execution is owner-approved; savings verified via AWS billing. Scope: AWS EC2/VM compute only (LLM, GPU, storage/ECR, network transfer are separate tracks). Sequence: Identify -> Schedule -> Right-size -> Consolidate -> Migrate/Modernise -> Dynamically Scale -> Commercially Commit. | 30-40% compute-cost reduction in 90 days; 100% VM inventory mapped to owner and application; >80% approved actions implemented; 0 critical incidents; savings validated via AWS billing. | High | aws;cost-optimisation;finops | 90 days
Story |  | AWS Compute Cost Optimisation Strategy (90-Day Operating Model) | Baseline & Visibility (VorteX + AWS inventory) | Deploy VorteX agents across AWS VMs and capture AWS inventory to build a cost baseline, map ownership and classify utilisation so every optimisation action is evidence-backed. | All VMs have VorteX agents capturing utilisation, runtime, ownership; 100% VM inventory mapped to owner and application; cost baseline established from AWS billing; VMs classified as idle/underutilised/overutilised/intermittent. | High | aws;visibility;vortex;baseline | Weeks 1-3
Story |  | AWS Compute Cost Optimisation Strategy (90-Day Operating Model) | Self-Service Grouping & Scheduling | Enable grouping, scheduled start/stop and component-level grouping so only required VMs run and non-production runtime is automated. | Self-service and component-level grouping available; scheduled start/stop configured for eligible non-production environments; idle VM removal executed for approved resources. | High | aws;scheduling;grouping | Weeks 4-8
Story |  | AWS Compute Cost Optimisation Strategy (90-Day Operating Model) | Right-Size & Consolidate | Downsize oversized instances and consolidate compatible workloads onto fewer right-sized hosts so capacity follows actual demand. | Oversized instances identified and right-sized after owner approval; compatible workloads consolidated onto fewer right-sized hosts; no critical incidents introduced. | High | aws;right-sizing;consolidation | Weeks 4-8
Story |  | AWS Compute Cost Optimisation Strategy (90-Day Operating Model) | EKS + OS Optimisation | Move eligible native Kubernetes workloads to Amazon EKS and reduce RHEL-based worker dependency where Amazon Linux is sufficient (draft example ~39% per-instance OS licence saving). | Eligible native K8s workloads migrated to EKS; RHEL workers replaced with Amazon Linux where sufficient; OS licence saving measured and reported. | Medium | aws;eks;os-optimisation | Weeks 4-8
Story |  | AWS Compute Cost Optimisation Strategy (90-Day Operating Model) | CLB / ELB -> NLB Consolidation | Shift suitable traffic from multiple CLBs/ELBs to a consolidated NLB model per environment to reduce load-balancer cost through consolidation. | Suitable traffic migrated to a consolidated NLB per environment; LB inventory reduced; conversions tracked in the scorecard. | Medium | aws;load-balancer;nlb | Weeks 4-8
Story |  | AWS Compute Cost Optimisation Strategy (90-Day Operating Model) | Karpenter Dynamic Scaling for EKS Workloads | Use Karpenter to dynamically provision and consolidate EKS worker nodes for native Python, AI/ML and agentic workloads, avoiding permanently running worker nodes for intermittent processing. | Karpenter provisions worker nodes on demand and removes them when demand reduces; no over-provisioning 'just in case'; first Karpenter workloads onboarded and utilisation tracked. | Medium | aws;eks;karpenter;autoscaling | Weeks 4-8
Story |  | AWS Compute Cost Optimisation Strategy (90-Day Operating Model) | AI Recommendation Layer (VorteX + AWS Signals) | Build a custom AI agent using VorteX + AWS cost signals to continuously rank idle, underutilised, overutilised and oversized VMs with estimated savings and owner-approved actions. | Agent continuously identifies idle/underutilised/overutilised/oversized VMs; ranked actions produced with estimated savings; initial mode recommendation-only; production changes require owner validation, dependency assessment and approved change execution. | Medium | aws;ai;recommendations;vortex | Weeks 4-12
Story |  | AWS Compute Cost Optimisation Strategy (90-Day Operating Model) | Reserved Instance (Commercial) Strategy | Apply 1-year or 3-year commitments only to predictable, always-on workloads after scheduling, right-sizing, consolidation and dynamic scaling are complete, to avoid locking in excess capacity. | RI evaluation performed only after earlier levers complete; commitments applied to stable baseline capacity only; pricing validated via AWS Cost Explorer / Pricing Calculator before commitment. | Medium | aws;reserved-instances;commercial | Weeks 9-12
Story |  | AWS Compute Cost Optimisation Strategy (90-Day Operating Model) | Scale, Govern & Validate Savings | Expand the model to eligible environments, validate savings through AWS billing, publish the utilisation dashboard and govern recommendations as an ongoing operating discipline. | Model expanded to eligible environments; savings validated via AWS billing and dashboard; monthly scorecard published (baseline vs current cost, idle/underutilised VMs, non-business-hour runtime, right-sized/consolidated VMs, EKS/OS migrations, CLB->NLB conversions, Karpenter utilisation, RI baseline, billing-validated savings); 0 critical incidents. | High | aws;governance;validation;dashboard | Weeks 9-12