## Jira Import
Issue Type | Summary | Description | Priority | Labels | Epic Name | Epic Link | Project key | Components
Epic | Build a secure cloud-native delivery platform | Deliver an automated software supply chain that builds, assesses, remediates, deploys, scales, monitors, and protects containerized workloads. Definition of done: * The end-to-end path from source commit to EKS deployment is automated. * Vulnerable artifacts are blocked and secure artifacts are published. * Deployments are reconciled through GitOps. * Autoscaling, monitoring, dashboards, and runtime controls are operational. * Operating procedures and evidence for each control are documented. | High | secure-platform | Secure Cloud-Native Delivery Platform |  | SECPLAT | Platform Engineering
Story | Trigger Jenkins CI from GitHub commits | As a developer, I want commits to trigger the Jenkins pipeline so that every change is validated consistently. Acceptance criteria: * Commits to configured branches trigger the correct pipeline. * The pipeline checks out the exact triggering revision. * Trigger and checkout failures are visible to developers. | Medium | secure-platform |  | Secure Cloud-Native Delivery Platform | SECPLAT | Platform Engineering
Story | Build an immutable container image | As a platform engineer, I want the pipeline to build a versioned container image so that releases are reproducible and traceable. Acceptance criteria: * The image build runs only after source checkout succeeds. * Every image is tagged with an immutable revision identifier. * Build failures stop all downstream stages. | Medium | secure-platform |  | Secure Cloud-Native Delivery Platform | SECPLAT | Platform Engineering
Story | Generate a software bill of materials | As a security engineer, I want an SBOM generated for every image so that included software components are auditable. Acceptance criteria: * Syft generates an SBOM for each built image. * The SBOM is stored as a pipeline artifact and linked to the image revision. * Failure to generate the SBOM blocks promotion. | Medium | secure-platform |  | Secure Cloud-Native Delivery Platform | SECPLAT | Security
Story | Scan images for known vulnerabilities | As a security engineer, I want each image scanned for CVEs so that vulnerable artifacts cannot be promoted. Acceptance criteria: * Grype or Trivy scans the built image and its packages. * Configurable severity thresholds determine pass or fail. * Scan findings are retained and visible from the pipeline. * Images above the threshold do not reach the registry. | Medium | secure-platform |  | Secure Cloud-Native Delivery Platform | SECPLAT | Security
Story | Analyze vulnerability findings with AI | As a developer, I want vulnerability findings enriched with remediation guidance so that issues can be resolved efficiently. Acceptance criteria: * Failed scan findings are sent to the analysis engine without credentials or secrets. * Recommendations identify the affected component, safe target version, and rationale. * Recommendations link back to the originating image and scan. * Uncertain recommendations are clearly marked for manual review. | Medium | secure-platform |  | Secure Cloud-Native Delivery Platform | SECPLAT | Security
Story | Revalidate remediated builds | As a security engineer, I want remediated changes to repeat the build and security checks so that only verified fixes are promoted. Acceptance criteria: * A remediation starts a new pipeline execution. * The image, SBOM, and CVE scan are regenerated. * Promotion occurs only when the configured security gate passes. * Retry limits prevent an uncontrolled remediation loop. | Medium | secure-platform |  | Secure Cloud-Native Delivery Platform | SECPLAT | Security
Story | Publish approved images to the registry | As a release engineer, I want approved images published to a registry so that deployment uses trusted artifacts. Acceptance criteria: * Only images that pass required pipeline gates are pushed. * Registry authentication uses managed credentials. * Published image digests and SBOM references are recorded. * Mutable tag overwrite is prevented for release images. | Medium | secure-platform |  | Secure Cloud-Native Delivery Platform | SECPLAT | Platform Engineering
Story | Deploy approved images through GitOps | As a platform engineer, I want approved image changes reconciled through GitOps so that cluster state is declarative and auditable. Acceptance criteria: * Deployment manifests reference an approved immutable image digest. * Changes are reviewed and committed to the GitOps source of truth. * The GitOps controller reconciles the change to EKS. * Failed reconciliation reports actionable status and supports rollback. | Medium | secure-platform |  | Secure Cloud-Native Delivery Platform | SECPLAT | Platform Engineering
Story | Provision EKS capacity with Karpenter | As a platform engineer, I want Karpenter to provision cluster nodes dynamically so that workloads receive capacity without static overprovisioning. Acceptance criteria: * Pending eligible workloads trigger node provisioning. * Node selection follows configured workload, security, and cost constraints. * Unused capacity is consolidated without disrupting protected workloads. * Provisioning and consolidation events are observable. | Medium | secure-platform |  | Secure Cloud-Native Delivery Platform | SECPLAT | Platform Engineering
Story | Collect platform and workload metrics | As an SRE, I want Prometheus to collect platform and workload metrics so that service health and capacity can be measured. Acceptance criteria: * Prometheus discovers and scrapes the agreed EKS targets. * Collection failures and storage pressure generate alerts. * Metric retention and access controls meet platform requirements. * Karpenter and workload health metrics are available for querying. | Medium | secure-platform |  | Secure Cloud-Native Delivery Platform | SECPLAT | Observability
Story | Provide operational Grafana dashboards | As an SRE, I want Grafana dashboards for delivery and runtime health so that teams can identify issues quickly. Acceptance criteria: * Dashboards show deployment, cluster, node, and workload health. * Dashboard panels use the Prometheus data source and document their queries. * Access follows least privilege. * Dashboard definitions are version controlled. | Medium | secure-platform |  | Secure Cloud-Native Delivery Platform | SECPLAT | Observability
Story | Enforce runtime security policies | As a security engineer, I want runtime policies enforced in EKS so that deployed workloads operate within approved boundaries. Acceptance criteria: * Policies cover privileged execution, image provenance, and other agreed controls. * Enforcement mode and exceptions are documented and auditable. * Violations generate actionable alerts. * Policy changes are tested before production enforcement. | Medium | secure-platform |  | Secure Cloud-Native Delivery Platform | SECPLAT | Security